## Semester Plan
Starting | Task | Notes
15.10 | Disposition | DISPO OK!
03.10 | Coding | Research Literature, Start with coding
10.10 | Coding | Research Literature, Start with coding
17.10 | Final Dispo | Dispo Deadline + continue coding
24.10 | Coding | Continue coding
31.10 | Coding | Continue coding | --> change of plan because of heavy weighted mid-term exams | 31.10 | Break | Study for Mid-terms
07.11 | Coding | Continue coding |  | 07.11 | Coding/Start Writing Paper | Finish Coding + Start Writing Paper
14.11 | Writing Paper | Write Paper |  | 14.11 | Writing Paper | Write Paper
21.11 | Writing Paper |  |  | 21.11 | Writing Paper
28.11 | Writing Paper |  |  | 28.11 | Finished draft, send to Stefan + Prepare Presentation
05.12 | Finished draft, send to Stefan + Prepare Presentation |  |  | 05.12 | Implement corrections
11.12 | Hand in finished Project + Prepare Presentation |  |  | 11.12 | Hand in finished Project + Prepare Presentation
19.12 | Presentation (Gs c7, 8:45 9:15) |  |  | 19.12 | Presentation (Gs c7, 8:45 9:15)